## 📅 Timeline
PROVIDER CREDENTIALING TIMELINE · The Marketing Pros
📅 START DATE → |  |  | 2026-08-04 | ← Change this date. All milestone dates update automatically.
OVERALL PROGRESS
PHASE | TASK | OWNER | WEEK TARGET | TARGET DATE | TODAY? | DAYS TO DUE | STATUS | COMPLETE DATE | NOTES
Pre-App Prep | Collect all provider documents | Practice Mgr | Week 1 |  |  |  | Not Started
Pre-App Prep | Verify NPI — check NPPES registry | Practice Mgr | Week 1 |  |  |  | Not Started
Pre-App Prep | Create / update CAQH ProView profile | Cred Specialist | Week 1 |  |  |  | Not Started
Pre-App Prep | Upload all documents to CAQH | Cred Specialist | Week 1 |  |  |  | Not Started
Pre-App Prep | Grant payer authorizations in CAQH | Cred Specialist | Week 1 |  |  |  | Not Started
Pre-App Prep | Complete CAQH attestation | Provider | Week 1 |  |  |  | Not Started
Pre-App Prep | Build payer priority matrix — rank applications | Practice Mgr | Week 1 |  |  |  | Not Started
Pre-App Prep | Confirm malpractice coverage is adequate | Practice Mgr | Week 2 |  |  |  | Not Started
Submission | Submit Medicare PECOS enrollment | Cred Specialist | Week 2 |  |  |  | Not Started
Submission | Submit Medicaid enrollment (state portal) | Cred Specialist | Week 2 |  |  |  | Not Started
Submission | Submit BCBS application | Cred Specialist | Week 2 |  |  |  | Not Started
Submission | Submit Aetna application | Cred Specialist | Week 3 |  |  |  | Not Started
Submission | Submit UnitedHealthcare application | Cred Specialist | Week 3 |  |  |  | Not Started
Submission | Submit Cigna application | Cred Specialist | Week 3 |  |  |  | Not Started
Submission | Submit additional payer applications | Cred Specialist | Week 4 |  |  |  | Not Started
Submission | Log all confirmation numbers + contacts | Cred Specialist | Week 4 |  |  |  | Not Started
Follow-Up | Follow up with all payers — 1st check | Cred Specialist | Week 5 |  |  |  | Not Started
Follow-Up | Re-attest CAQH if approaching 120-day expiry | Provider | Week 8 |  |  |  | Not Started
Follow-Up | Follow up with all payers — 2nd check | Cred Specialist | Week 8 |  |  |  | Not Started
Follow-Up | Follow up with all payers — 3rd check | Cred Specialist | Week 11 |  |  |  | Not Started
Follow-Up | Escalate any application >90 days no movement | Cred Specialist | Week 13 |  |  |  | Not Started
Follow-Up | Follow up with all payers — 4th check | Cred Specialist | Week 14 |  |  |  | Not Started
Go-Live | Get written effective date — each payer | Cred Specialist | On Approval | On Approval |  |  | Not Started
Go-Live | Add provider to PM / billing system | Billing Mgr | On Approval | On Approval |  |  | Not Started
Go-Live | Verify EDI/ERA enrollment active | Billing Mgr | Week 1 |  |  |  | Not Started
Go-Live | Submit test claim — verify it processes | Billing Mgr | Week 1 |  |  |  | Not Started
Go-Live | Confirm fee schedule rates match contract | Billing Mgr | Week 2 |  |  |  | Not Started
Go-Live | Update payer provider directory listings | Cred Specialist | Week 4 |  |  |  | Not Started
Maintenance | Set re-credentialing reminders (2–3 yr cycles) | Cred Specialist | On Approval | On Approval |  |  | Not Started
Maintenance | Set CAQH re-attestation recurring (90 days) | Provider | On Approval | On Approval |  |  | Not Started
Maintenance | Set license + DEA renewal reminders (60d out) | Practice Mgr | On Approval | On Approval |  |  | Not Started
Maintenance | Quarterly underpayment audit vs. contract | Billing Mgr | Week 13 |  |  |  | Not Started
Maintenance | Annual payer contract review | Practice Mgr | Week 52 |  |  |  | Not Started
Formulas:
TODAY? = IF([TARGET DATE]="On Approval","",IF(AND(TODAY()>=[TARGET DATE],TODAY()<[TARGET DATE]+7),"▶ NOW",""))
DAYS TO DUE = IF([TARGET DATE]="On Approval","",[TARGET DATE]-TODAY())